## Schedule
Activity Code | Activity Name | Planned Start | Planned End | Planned Progress % | Actual Progress %
F001 | Pile Foundation | 2026-03-01 | 2026-06-20 | 100 | 95
F002 | Pier Construction | 2026-04-01 | 2026-07-05 | 80 | 72
F003 | Deck Slab Preparation | 2026-05-15 | 2026-07-20 | 60 | 35
F004 | Approach Road | 2026-06-01 | 2026-07-31 | 40 | 20
F005 | Drainage Works | 2026-06-15 | 2026-07-31 | 30 | 18

## Dependencies
Predecessor | Successor | Dependency Type
F001 | F002 | Finish-to-Start
F002 | F003 | Finish-to-Start
F003 | F004 | Finish-to-Start
F004 | F005 | Finish-to-Start