## Schedule
Activity Code | Activity Name | Planned Start | Planned Finish | Planned Progress | Actual Progress | Status | Predecessor Codes | Dependency
W001 | Utility Survey & Marking | 2026-03-01 | 2026-03-10 | 100 | 0 | NOT_STARTED |  | Independent
W002 | Trench Excavation | 2026-03-01 | 2026-04-15 | 88 | 0 | NOT_STARTED | W001 | W001
W003 | DI Pipeline Laying | 2026-04-01 | 2026-05-20 | 72 | 0 | NOT_STARTED | W002 | W002
W004 | Valve Chamber Construction | 2026-05-01 | 2026-06-05 | 61 | 0 | NOT_STARTED | W003 | W003
W005 | Service Connection Transfer | 2026-05-15 | 2026-06-20 | 42 | 0 | NOT_STARTED | W003 | W003
W006 | Pressure Testing & Commissioning | 2026-06-10 | 2026-06-30 | 18 | 0 | NOT_STARTED | W004,W005 | W004 + W005

## Field Guide
Field | Meaning
Activity Code | Stable identifier used to match execution evidence to the schedule.
Activity Name | Scheduled work package/activity name.
Planned Start | Baseline start date.
Planned Finish | Baseline finish date.
Planned Progress | Baseline progress percentage used for planned-vs-actual variance.
Actual Progress | Initial trusted actual state; starts at 0 before evidence ingestion.
Status | Initial schedule status before field evidence is processed.
Predecessor Codes | Activities that should precede this activity.
Dependency | Human-readable dependency description.